## INSTRUCTIONS
PROCEDURE | INSTRUCTIONS
1 | Create a new Domain User with Local Administrator on all systems privileges for CPT Use
2 | Configure PERSISTENT Endgame sensors IAW 262COS-ENDGAME-SOP-001
3 | Configure a TFPlenum host agent package with Winlogbeat, Sysmon, and Endgame configured to point the DIP EXTERNAL IP
4 | Perform host discovery and management port scans IAW 262COS-NA-SOP-001 to fill and verify targeting details within the TARGETS worksheet tab
5 | Verify credentials by interactively logging into one host per deployment group
6 | Deploy Winlogbeat and Sysmon in batches to the different deployment groups IAW 262COS-HA-SOP-002
7 | Deploy Auditbeat in batches to the different deployment groups IAW 262COS-HA-SOP-002
8 | Deploy Endgame in batches to the different deployment groups with the appropriate sensor installer and an initial DO-NOTHING policy IAW 262COS-HA-SOP-002
9 | In the Endgame UI, after a successful DO-NOTHING policy install - apply either the DETECT-ONLY or DETECT+STREAM policy based on host specific information in the TARGETS worksheet tab
10 | Interactively logon to hosts targeted for Filebeat deployment in order to identify log files to be collected
11 | Configure unique filebeat.yml files to collect targeted log files and forward to the DIP EXTERNAL IP over TCP/5045
12 | Deploy Filebeat in batches to the different deployment groups IAW 262COS-HA-SOP-002

## TARGETS
DEPLOYMENT GROUP | HOSTNAME | DOMAIN | MANAGEMENT IP | OPERATING SYSTEM | USERNAME | PASSWORD | SYSMON | ENDGAME | WINLOGBEAT | AUDITBEAT | FILEBEAT | LEGEND
1 | DC | FAKENET.USAF.MIL | 150.151.9.250 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X |  |  | X | Deploy with normal procedures
1 | FILE | FAKENET.USAF.MIL | 150.151.9.252 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X |  |  | X* | Anticipate issues
1 | WEB | FAKENET.USAF.MIL | 150.151.55.253 |  | <CREATE USER> | <CREATE USER> | ? | ? | ? | ? | CONFIG | CONFIG | Manual configuration required
1 | EXCHANGE | FAKENET.USAF.MIL | 150.151.55.251 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X |  |  | STREAM | Deploy with Endgame streaming
2 | RF-C2B-6-1 | FAKENET.USAF.MIL | 150.151.6.1 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X |  |  | ? | Prepare to deploy due to unknown OS
2 | RF-C2B-6-2 | FAKENET.USAF.MIL | 150.151.6.2 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-3 | FAKENET.USAF.MIL | 150.151.6.3 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-4 | FAKENET.USAF.MIL | 150.151.6.4 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-5 | FAKENET.USAF.MIL | 150.151.6.5 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-6 | FAKENET.USAF.MIL | 150.151.6.6 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-7 | FAKENET.USAF.MIL | 150.151.6.7 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-8 | FAKENET.USAF.MIL | 150.151.6.8 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-9 | FAKENET.USAF.MIL | 150.151.6.9 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-10 | FAKENET.USAF.MIL | 150.151.6.10 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-11 | FAKENET.USAF.MIL | 150.151.6.11 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-12 | FAKENET.USAF.MIL | 150.151.6.12 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-13 | FAKENET.USAF.MIL | 150.151.6.13 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-14 | FAKENET.USAF.MIL | 150.151.6.14 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-15 | FAKENET.USAF.MIL | 150.151.6.15 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-16 | FAKENET.USAF.MIL | 150.151.6.16 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-17 | FAKENET.USAF.MIL | 150.151.6.17 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-18 | FAKENET.USAF.MIL | 150.151.6.18 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-19 | FAKENET.USAF.MIL | 150.151.6.19 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
2 | RF-C2B-6-20 | FAKENET.USAF.MIL | 150.151.6.20 | Windows (?) | <CREATE USER> | <CREATE USER> | X | X | X
3 | C2B-Fedora-01 |  | 150.151.6.51 | Fedora (?) | Admin | password1 |  | STREAM |  | X*
3 | C2B-Fedora-02 |  | 150.151.6.52 | Fedora (?) | Admin | password1 |  | STREAM |  | X*
3 | C2B-Fedora-03 |  | 150.151.6.53 | Fedora (?) | Admin | password1 |  | STREAM |  | X*
3 | C2B-Fedora-04 |  | 150.151.6.54 | Fedora (?) | Admin | password1 |  | STREAM |  | X*
3 | C2B-Fedora-05 |  | 150.151.6.55 | Fedora (?) | Admin | password1 |  | STREAM |  | X*
4 | C2B-Ubuntu-01 |  | 150.151.6.56 | Ubuntu (?) | Admin | password1 |  | STREAM |  | X*
4 | C2B-Ubuntu-02 |  | 150.151.6.57 | Ubuntu (?) | Admin | password1 |  | STREAM |  | X*
4 | C2B-Ubuntu-03 |  | 150.151.6.58 | Ubuntu (?) | Admin | password1 |  | STREAM |  | X*
4 | C2B-Ubuntu-04 |  | 150.151.6.59 | Ubuntu (?) | Admin | password1 |  | STREAM |  | X*
4 | C2B-Ubuntu-05 |  | 150.151.6.60 | Ubuntu (?) | Admin | password1 |  | STREAM |  | X*
5 |  |  | 150.150.7.41 | Linux scadabr 4.9.0-6amd64 #1 SMP Debian 4.9.88-1+deb9u1 | scadabr | password2 |  | STREAM |  | X*
6 |  |  | 150.150.7.81 | Windows 7 | john | password3 | X* | X* | X
7 |  |  | 150.150.7.100 | Windows 10 | clara | password4 | X | X | X
8 |  |  | 150.151.7.51 | Ubuntu 20.04.4 LTS | clara | password4 |  | STREAM |  | X*
9 |  |  | 150.151.7.52 | Ubuntu 20.04.4 LTS | clara | password5 |  | STREAM |  | X*
9 |  |  | 150.151.7.53 | Ubuntu 20.04.4 LTS | clara | password6 |  | STREAM |  | X*
9 |  |  | 150.151.7.54 | Ubuntu 20.04.4 LTS | clara | password7 |  | STREAM |  | X*
9 |  |  | 150.151.7.55 | Ubuntu 20.04.4 LTS | clara | password8 |  | STREAM |  | X*
9 |  |  | 150.151.7.56 | Ubuntu 20.04.4 LTS | clara | password9 |  | STREAM |  | X*
9 |  |  | 150.151.7.82 | Ubuntu 20.04.4 LTS | clara | password10 |  | STREAM |  | X*
9 |  |  | 150.151.7.83 | Ubuntu 20.04.4 LTS | clara | password11 |  | STREAM |  | X*
9 |  |  | 150.151.7.84 | Ubuntu 20.04.4 LTS | clara | password12 |  | STREAM |  | X*
10 |  |  | 150.151.7.102 | Ubuntu 18.04.6 LTS | plc | 1234abc |  | STREAM |  | X*
10 |  |  | 150.151.7.103 | Ubuntu 18.04.6 LTS | plc | 1234abc |  | STREAM |  | X*
10 |  |  | 150.151.7.104 | Ubuntu 18.04.6 LTS | plc | 1234abc |  | STREAM |  | X*
10 |  |  | 150.151.7.105 | Ubuntu 18.04.6 LTS | plc | 1234abc |  | STREAM |  | X*
10 |  |  | 150.151.7.106 | Ubuntu 18.04.6 LTS | plc | 1234abc |  | STREAM |  | X*
11 |  |  | 150.151.7.85 | Windows 10 | HMI | !@QAZX12qwaszx | X | X | X

## CONTINGENCIES
TRIGGER | IMPACT | RESPONSE
Scripted agent deployment fails after 30min of troubleshooting | Time to complete agent deployment task is increased | Perform agent deployment manually
Endgame is unable to install on a host after 30min of troubleshooting | Alerting on MCA will not be available - manual analysis must be conducted to detect MCA | Rely on Auditbeat for system event logging and manual analysis - rely on active Metasponse collections if Auditbeat is also unavailable
Sysmon is unable to install on a host after 30min of troubleshootingy | Detailed system event logging will not be available - alerts detecting MCA will be degraded | Rely on native Windows log for system event logging
Winlogbeat is unable to install on a host after 30min of troubleshooting | Detailed system event logging will not be available - alerts detecting MCA will be degraded | Rely on Endgame Stream for system event logging and alerting - rely on active Metasponse collections if Endgame is also unavailable
Auditbeat is unable to install on a host after 30min of troubleshooting | Detailed system event logging, user audits, and software audits will not be available | Rely on Endgame Stream for system event logging and alerting - rely on active Metasponse collections if Endgame is also unavailable
Installation of a host agent causes system instability | Mission Partner system, system event logging/streaming, and MCA alerting is degraded | Uninstall the host agent
New user accounts are not able to be created for CPT use after 30min of troubleshooting | The CPT will not have dedicated privileged accounts to perform interactive actions on the MPNet | Utilize existing administrator use accounts for interactive actions